## OVC
SERVE SDP 2012-15 Results Framework
Programme: SERVE Development Programme
Time Period: 2012-2016
Geographic Focus: South Africa, Mozambique & Zimbabwe
Overall Goal: Reduce vulnerability and improve livelihood security for poor children, young people, women and men in targeted communities in RSA, Moz & Zim
Outcome 1: Reduced vulnerability and improved quality of life for OVC in targeted communities in Rustenburg, RSA
Objectives: (1) Strengthen capacity of families/community based response to care for children in Godisanang OVC Programme, RSA
Result | Target Beneficiaries | Key Performance Indicators | Baseline | Target 2012 | Results 2012 | Target 2013 | Results 2013 | Target 2014 | Results 2014 | Target 2015 | Results 2015 | Target 2016
1.1 Tapologo OVC (TOVC) Programme successfully strengthens target communities to meet the needs of 550 identified OVC (272 female, 278 male) through a community based response | 550 OVC identified by OVC Programme and their families in communities of Freedom Park, Boitekong & Ledig. (49% female, 51% male; 62% aged 0-12, 38% aged 12-18) | 1. % of registered OVC receiving a service, measured at 6 month intervals | 1. 99.8% of registered OVC in 3 target communities of TOVC receiving a service (Aug, 2013) | 80% (Previously funded GOVC Programme) | June 2012 - 75% Dec 2012 - 60% Yearly Average of 68% (Previously funded GOVC Programme) Off track | TOVC: 100% | TOVC: 103% (564 OVC) Average number of registered OVC receiving a service between Sept-Dec 2013 was 564 (51% male 49% female; 0-12 yrs - 61% 12-18 yrs - 39%) ON TRACK | TOVC: 103% (564 OVC) | TOVC: 110% (603 OVC) (52% male, 48% female; 0-12 years -60%, 12-18 years - 40%) ON TRACK | TOVC: 110% (605 OVC) | TOVC: 111% (610 OVC) ON TRACK (51% male, 49% female; 0-2 yrs - 4%; 3-4 yrs - 9%; 5-11 yrs - 47%; 12-18 yrs - 40%) | TOVC: 111% (610 OVC)
1.2 3 TOVC Daycare Centres renovated/expanded by 2016, helping to retain current beneficiaries/meet increased demand | 550 OVC identified by OVC Programme and their families in communities of Freedom Park, Boitekong & Ledig. (49% female, 51% male; 62% aged 0-12, 38% aged 12-18) | 1. Completion of physical work at each centre, measured every year 2. % change in daily attendance at renovated OVC Centres, measured at 6 month intervals | 1. 3 centres require work 2. Average of 550 OVC using the 3 centres (average of 53% female, 47% male). Newly Funded TOVC Programme: > Freedom Park: 216 OVC attending (49% female/51% male), Aug 2013 > Boitekong: 218 OVC attending (46% female/54% male), Aug 2013 > Ledig: 115 attending OVC (56% female/44% male), Aug 2013 | 1. Robega OVC Centre; Boitekong OVC Centre 2. 440 OVC (Previously funded GOVC Programme) | 1(a) Renovation, expansion work completed at Robega & Boitekong - on track 2 (b). Robega: > Max capacity increased by 75%; > 73% of registered users (94/129) at Robega using centre on a daily basis - 47% male, 53% female; Boitekong: > Max capacity increased by 33% to 100+; > 40% of registered users (93/237) at Boitekong using centre on a daily basis - 51% male, 49% female Total of 332 OVC using Centres as of Dec 2012 (53% female, 47% male; 41% aged 0-12, 59% aged 12+) Off Track | 1. Chaneng OVC Centre; Lefaragatle OVC Centre; 2. Average of 385 OVC across 6 centres > Chaneng: 5% increase > Lefaragatle: 5% increase (Old targets under GOVC Programme) | Due to switch from GOVC to TOVC Programme, confirmed in October 2013, no work was done on any OVC Centres in 2013. Work planned for 2014 & 2015 with targets set | 1. Freedom Park OVC Centre upgrade completed 2. Beneficiary numbers maintained at average of 216 OVC per month at Freedom Park OVC Centre | 1. Renovation work completed at Freedom Park OVC Centre & Ledig OVC Centre - ON TRACK 2. Freedom Park - 7% increase in benficiary numbers to average of 230 OVC per month (51% male, 49% female) Ledig - 35% increase in beneficiary numbers to average of 155 OVC per month (48% male, 52% female) ON TRACK | 1.Boitekong Centre upgrades completed 2.Beneficiary numbers are maintained at average of 218 OVC per month at Boitekong OVC Centre | 1. Upgrades & renovations completed at all OVC Centres by O & M Team. SERVE volunteers contributed to extensive upgrades at Freedom Park Centre - ON TRACK 2. Beneficiary numbers (average monthly) at each Daycare Centre: > FP: 205 OVC > Boitekong: 217 OVC > Ledig: 192 OVC ON TRACK (51% male, 49% female; 0-2 yrs - 4%; 3-4 yrs - 9%; 5-11 yrs - 47%; 12-18 yrs - 40%) | 1. FP/Ledig/ Boitekong Centres maintained 2. Beneficiary numbers at each Daycare Centre maintained
1.3 480 OVC (80% of beneficiaries) reach and maintain adequate nutritional status by 2016 (Adequate status determined by WHO standards) | 550 OVC from communities of Freedom Park, Boitekong & Ledig who are eligible to attend the Tapologo OVC Daycare Centres. (49% female, 51% male; 62% aged 0-12, 38% aged 12-18) | 1. % of stunted OVC, measured at six month intervals; 2. % OVC classified as 'under' or 'over' the 'ideal' BMI range for their particular age; All results compared to WHO standards using WHO AnthroPlus Software | 1. 72% of OVC stunted (Nov, 2013). Occurence higher amongst male OVC (81%) than female OVC (63%) 2. 31% of all OVC classified as 'under' BMI range for their age. Occurence higher amongst females (47%) than males (53%) | N/A - Baseline was establised in Q4 2012 | 1. 49% of OVC stunted (Sept, 2012). Occurrence higher amongst males (55%) than females (45%); 2. 41% of OVC classified as 'under' (27%) or 'over' (14%) BMI range for their particular age. Occurrence higher amongst males (45%) than females (39%) Please note that these results relate to different communities under the GOVC Programme | No targets set for TOVC in 2013 due to switch to programme in October 2013. The first monitoring exercise was a baseline setting exercise for the new Daycare Centres carried out in Nov 2013 | 1. 72% of all OVC stunted on TOVC Programme - Nov '13 (occurence higher amongst male OVC - 81%, than female OVC - 63% - OFF TRACK; 2. 31% of all OVC (Nov '13) classified as 'under' BMI range for their age. Occurence higher amongst females (47%) than males (43%) - ON TRACK * For stunted growth figures, 47% are classified as "moderately" stunted, 25% are "severly" stunted (52% female, 48% male, 63% aged 0-12, 37% aged 12 - 18 ) | 1. 72% of OVC stunted; 2. 25% of OVC classified as 'under' BMI range for their age; | 1. Average of 59% of all OVC Stunted (occurence higher amongst male OVC - 62%, than female OVC - 56%) - ON TRACK * Of the 59% who are stunted, 53% are moderately stunted & 6% are severely stunted 2. Average of 18% of all OVC classified as "under" BMI range for their age. Occurence slightly higher amongst males (22%) than females (21%); Average of 17% of all OVC classified as "over" BMI range. Occurence slightly higher amongst females (17%) than males (16%) - ON TRACK | 1. 60% of OVC stunted; 2. 15% of OVC classified as 'under' BMI range for their age; 15% of OVC classified as "over" BMI range for their age | 1. 49% of OVC stunted 2. 68% of OVC, aged 10-19 years, classified as "ideal" BMI range for their age; 23% are under ideal BMI range for their age; 9% are over ideal BMI range for their age; 71% of OVC, aged 0-10 years of age, at ideal "weight for age"; 23% of OVC under 10 years of age under weight; 9% of OVC under 10 years of age over weight; (51% female; 49% male 4% aged 2-5 years; 57% aged 6-12 years; 31% aged 13-18 years) SEE NOTE 1 | 1. 50% of OVC stunted (adj); 2. 80% of OVC classified as 'ideal' BMI range for their age or 'ideal weight for age' SEE NOTE 1
1.4 Evidence based research available to promote lessons learned from GOVC intervention model which is a partnership between government and NGO | OVC Policymakers in Southern Africa and Irish NGOs involved in OVC Programmes | 1. Incidences of replication of gov/NGO model leading directly from research paper | 1. No existing research into this partnership | Research commissioned by Q4 2012 | Terms of Reference being agreed and partner institution being recruited. Will be commissioned by Q2 2013 | Research completed by Q4 2013 and disseminated | Due to breakdown of partnership between Tapologo and Bafokeng on GOVC Programme (communicated to Irish Aid in July 2013), this research was not possible. Alternative research & evaluation work done with YA Zimbabwe & Tsholofelo SEE NOTE 4 | N/A | N/A | N/A | N/A | N/A
Programme Outputs 2012-2016
Target 1.1 At least 23 Child Care Workers (CCW) working on TOVC Programme, contributing towards monthly average of 41,000 interventions for OVC
2012 Result 1.1: Average of 14 CCWs working on GOVC Programme in 2012, contributing towards 108,616 interventions - on track
2013 Result 1.1:22 CCWs, 1 Child Care Coordinator and 1 OVC Manager working on TOVC Programme in 2013, contributing towards monthly average of 36,400 interventions - off track
2014 Result 1.1: Average of 20 CCWs, 1 Child Care Coordinator and 1 OVC Manager working on TOVC Programme in 2014, contributing towards monthly average of 23,729 interventions
2015 Result 1.1: Average of 25 CCWs working on TOVC Programme in 2015, contributing towards monthly average of 26,554 interventions
Target 1.2 Average of 2,146 food & nutrition interventions made each month. Food & nutrition inverventions account for 15% of total interventions on TOVC Programme
2012 Result 1.2: Average of 2,400 food & nutrition interventions made each month in 2012. Food & nutrition interventions account for 27% of total interventions in 2012 - on track
2013 Result 1.2:Average of 1,934 food & nutrition interventions made each month in 2013. Food & nutrition interventions account for 5% of total interventions in 2013 - off track
2014 Result 1.2: Average of 3,839 food & nutrition interventions made each month in 2014. Food & nutrition interventions account for 18% of total interventions - on track
2015 Result 1.2: Average of 5,609 food & nutrition interventions made each month in 2015. Food & nutrition interventions account for 21% of total interventions - on track
Target 1.3 Improved physical infrastructure at 3 Daycare Centres for TOVC Programme
2012 Result 1.3: Improved physical infrastructure at 2 Daycare Centres for GOVC Programme - on track
2013 Result 1.3: No work undertaken in 2013 due to switch from GOVC to TOVC OVC centre sites
2014 Result 1.3: Renovations made to Freedom Park OVC Centre and painting work completed; Kitchen renovated at Ledig OVC Centre - On Track
2015 Result 1.3: Renovations undertaken across all OVC Centres by O & M Team. SERVE Volunteers contributed to FP OVC Centre Upgrades - complete refurb of kicthen - On Track
Target 1.4 Completion of one research paper into GOVC intervention model by Q2 2013
2012 Result 1.4: More extensive research will take place than originally planned, will be completed by Q3 2013 - off track
2013 Result 1.4: Not completed due to switch from GOVC to TOVC Programme (request to remove Result from Framework)
Underlying Assumptions/Contingencies
Result 1.1: CCW remain motivated to implement demanding OVC Programme/ Regular HR assessments & appropriate remuneration levels in place
Result 1.2: Building programme will not be delayed by delivery or construction delays/ Experienced construction & engineering team available at Tapologo
Result 1.3: Tapologo can meet high recurring cost of food & nutrition component/ Widening donor base and improved reporting to donors at the outcome level
Result 1.4: Researcher can access relevant personnel at government level/Working through Tapologo and using their contacts
Sources of Information (All available from SERVE upon request)
Result 1.1: Tapologo TOVC Quarterly Reports which include quantitative & qualitative information on programme. Information provided on number of beneficiaries, number & type of interventions
Result 1.2: KPI 1: SERVE reporting templates (completed during volunteering programme & monitoring visits); KPI 2: Tapologo beneficiary numbers per centre, updated monthly
Result 1.3: Direct Tapologo monitoring (Dec 2013), using template to gather age, gender, weight and height of OVC. Analysis of results completed using WHO AnthroPlus software to assess BMI status compared with international standards
Sample size of 155 OVC (Gender: 52% female; 48% male Age: 2-5 years-13%; 5-12 years-55%; 12-18 years-32%)
Result 1.4: N/A

## HIV-AIDS
SERVE SDP 2012-15 Results Framework
Programme: SERVE Development Programme
Time Period: 2012-2016
Geographic Focus: South Africa, Mozambique & Zimbabwe
Overall Goal: Reduce vulnerability and improve livelihood security for poor children, young people, women and men in targeted communities in RSA, Moz & Zim
Outcome 2: Enhanced levels of HIV/AIDS healthcare in 9 target communities and young people in target communities empowered to make better choices regarding their sexual & reproductive health
Objectives: (2) Increase access to holistic HIV/AIDS care targeting the most vulnerable communities in Rustenburg, RSA
(4) Improve and expand Life Skills Training education in TVET programmes
Result | Target Beneficiaries | Key Performance Indicators | Baseline | Target 2012 | Results 2012 | Target 2013 | Results 2013 | Target 2014 | Results 2014 | Target 2015 | Results 2015 | Target 2016
2.1 Nine Wellness Clinic providing comprehensive HIV/AIDS care to 9 target communities by 2016 | People with HIV who use Wellness Clinics in communities of Boitekong, Chaneng, Freedom Park, Kanana, Mfidwike, Phokeng, Photsaneng, Tlaseng, Tapologo Centre | 1. Completion of physical work at each Clinic, measured every year 2. % change in number of patients "in care" in each clinic per month 3. (i) Ratio of clinic patients/total community population 3. (ii) Ratio of clinic patients/estimated HIV/AIDS rate In 2016, KPI 3 updated to: 3 (i) Average number of people accessing services at Wellness Centres; 3 (ii) ARV Adherence Rate of Tapologo patients SEE NOTE 2 | 1. 9 centres require work 2. Average figures over 6 months (2012): Boitekong - 582; Freedom Park - 296; Phokeng - 315; Kanana - 259; Mfidwike - 228; Photsaneng - 38; Tlaseng - 253; Ledig - 274, Chaneng - 286; 3 (i) Average of 1,447 people using 3 new services at Wellness Centres (2015); 3 (ii) 85% ARV Adherence Rate amongst Tapologo patients (2015); SEE NOTE 2 | 1.Freedom Park Clinic, Kanana Clinic, Mfidwike Clinic, Photsaneng Clinic 2. 5% increase in target clinics 3. No target was set for 2012, as baseline was not to be completed until Q3 2012. The reliability and accuracy of this indicator is in doubt. Removed in 2014 | 1. Renovation, expansion work done at Freedom Park, Phokeng & Boitekong due to changed priorities - on track; 2. Boitekong - 561 (4% decrease in patients in care); > Freedom Park - 303 (2% increase in patients in care); > Phokeng - 279 (11% decrease in patients in care); Off Track | 1. Chaneng Clinic, Mfidwike Clinic & Photsaneng Clinic 2.Maintenance of patient in care numbers in target clinics | 1. Work undertaken at Chaneng Wellness Clinic, but not completed - OFF TRACK (SLIGHTLY) 2. 5% increase in patients at Chaneng Clinic (30% Male, 70% Female, 10% aged 0-19, 53% aged 20-45, 37% aged 45+, 87% of beneficiaries are HIV positive)- ON TRACK 3. After discussions with Tapologo it was agreed that this indicator was not viable. We request that this indicator be removed, and the impact of the clinics be addressed on a more qualitative basis (patient letters) in the Annual Report. | 1. Kanana Clinic, Tlaseng Clinic Locations changed to Chaneng, Ledig & Freedom Park 2. 5% increase in target clinics | 1. Renovation work done at Chaneng, Ledig & Freedom Park Wellness Clinics. Minor works to be completed - Slightly Off Track 2. Chaneng - 235 (18% decrease); Ledig - 147 (46% decrease); Freedom Park - 337 (14% increase) 32% Male, 68% female 8% 0-19 years 27% 20-35 yrs 65% 36 yrs + | 1. Kanana Clinic, Photsaneng Clinic 2. 5% increase in target clinics | 1. Tapologo O & M Team completed renovation and maintenance work at the following clinics: Ledig, Chaneng, Tlaseng, Kanana, Boitekong, Freedom Park & Mfidwike 2. Average User Nos of ART Service > Boitekong - 208 (64% decline from 2012 baseline) > Chaneng - 106 (63% decline) > Freedom Park - 236 (20% decline) > Kanana - 104 (60% decline) > Mfidikwe - 111 (51% decline) > Phokeng - 88 (72% decline) > Tlaseng - 100 (60% decline) 3 (i) After Reengineering process, 3 services added from August 2015. Accessed by average of 1,447 per month across 7 Wellness Centres. When combined with ART Service, average of 1,557 people per month using Wellness Centres 3 (ii) Adherence Rate of Tapologo patients is 0-14 yrs: 74%; 15-18 yrs: 71%; 19 yrs +: 89% 28% male, 72% female 0-18 yrs - 6%; 19-35 yrs - 28%; 36 yrs+ - 66% SEE NOTE 2 & Annual Report | 1. O & M work at 7 Clinics; (adj) 2. Maintenance of 2015 user numbers at benefitting clinics 3(i) Average of 1,550 people per month using 7 Wellness Centres; 3 (ii) Adherence Rates amongst patients accessing Wellness Centres: 0-14 yrs:75%; 15-18 yrs: 71%; 19 yrs +: 89% SEE NOTE 2
2.2 90% of young people make better choices regarding their sexual and reproductive health as a result of Life Skills Training being mainstreamed into TVET Programmes "Better choices" defined as UNAIDS definition of ABC | Between 2,700 (2012) and 3,400 (2013-15) young people per annum who are enrolled in TVET and academic programmes run by Tsholofelo in South Africa and Young Africa in Mozambique and Zimbabwe Gender disaggregation of 47% female, 53% male | 1. % of beneficiaries, measured at six month intervals, who report: A - abstinence, not engaging in sex or delaying first sex B - Being safer, by being faithful to one's partner or reducing the number of sexual partners C - Correct and consistent use of condoms 2. Comparison with control group not involved in Life Skills Training | 1. Zim: 70% report better choices (2011) Moz: 80% report better choices (2011) 76% report positive choices (2015) RSA: 83% report better choices (Dec 2012) 2. Zim Control Group: Moz Control Group: 75% RSA Control Group: 77% YA Moz 2015 Baselines > Beira Campus: 76% > Agri Tech: 66% | 1. Zim: 75% Moz: 80% RSA: 70% 2. No targets set for Control Groups (used for comparative purposes only) | 1. Zim: 69% (off track) Moz: 80% (on track) RSA: 83% (on track) 2. Zim Control Group: 63% Moz Control Group: 75% RSA Control Group: 77% | Zim: 75% (adj) Moz: 85% RSA: 85% (adj) | Zim: 91% (Dec 2013) - ON TRACK Moz: 76% (Dec 2013) - OFF TRACK RSA: 75% (Dec 2013) - OFF TRACK (Slightly) Zim: 52% male, 48% female, 68% aged 15-19, 32% aged 20+ Moz: 55% male, 45% female, 20% aged 16-19, 43% aged 20-25, 37% aged 26+ RSA: 43% male, 57% female, average age of 30 | Zim: 95% (adj) Moz: 85% (adj) RSA: 85% (adj) | Zim: 87% (Dec 2014) - OFF TRACK (Slightly) Moz: 85% (ON TRACK) RSA: Unable to complete monitoring work - see 2014 Report Zim: 40% male, 60% female, 26% aged 15-19, 47% aged 20-25, 27% aged 26+ Moz: 66% male, 34% female, 28% aged 16-19, 54% aged 20-25, 18% aged 26+ | Zim: 90% (adj) Moz: 90% (adj) RSA: N/A | Zim: 90% (Dec 2015) - ON TRACK Moz: Overall - 75% > 76% at Agri Tech > 75% at Beira Zim: 46% male, 54% female 10% aged 15-17 years; 64% aged 18-25 years; 26% aged 25 years + Moz: 35% male, 65% female 46% aged 17-20 years; 41% aged 21-25 years; 13% aged 26 years + | Zim: 90% Moz: 90% RSA: N/A
Programme Outputs 2012-2016
Target 2.1 Renovation and newly contructed Wellness Clinics in 9 squatter camps in Rustenburg , RSA
2012 Result 2.1: Renovation & expansion of 3 Wellness Clinics in Rustenburg, RSA - on track
2013 Result 2.1: Renovation & expansion of 3 Wellness Clinics in Rustenburg, RSA. However, the work at Chaneng is not yet finished - off track (slightly)
2014 Result 2.1: Renovation work undertaken at Chaneng, Ledig & Freedom Park Wellness Clinics. Minor works to be completed at Ledig and Chaneng Clinics due to impact of mining strike in 2014 - off track (slightly)
2015 Result 2.1: Tapologo O & M Team completed maintenance work at 7 Wellness Clinic sites in 2015 - on track
Target 2.2 Life Skills Training Programmes implemented in 4 TVET Programmes and accessed by 3,000 young people each year
2012 Result 2.2: LSTP mainstreamed into 4 TVET Programmes. Accessed by 3,000 + young people in 2012 - on track
2013 Result 2.2: LSTP mainstreamed into 4 TVET Programmes. Accessed by 221 adults and 3,000 young people in 2013 - on track
2014 Result 2.2: LSTP mainstreamed into 5 TVET Programmes. Accessed by 349 adults and 3,600 young people in 2014 - on track
2015 Result 2.2: LSTP mainstreamed into 5 TVET Programmes. Accessed by 437 adults and 3166 young people in 2015 - On Track
Target 2.2 Training on SERVE'S manualised youth leadership programme (GYTP) with 3 partners. Target of 120 youth leaders (60 male, 60 female) by 2015
2012 Result 2.2: To be completed with approximately 30 young people from one partner (Tsholofelo) in 2013 - on track
2013 Result 2.2: 30 young people involved with Tsholofelo completed GYTP Training in July 2013 - on track . HIV & AIDS mainstreamed into this programme which trains young people to become leaders in their communities
2014 Result 2.2: No training took place in 2014, SERVE'S Toolkit was updated - to be rolled out in 2015 - on track
2015 Result 2.2: Youth Leadership Training completed with 18 youth leaders in 2015
Underlying Assumptions/Contingencies
Result 2.1: Building programme will not be delayed by delivery or construction delays/ Experienced construction & engineering team available at Tapologo
Result 2.2: Primary data can be gathered consistently from highly mobile target group over the long term/ Develop database of graduates with contact details. Establishment of easy to use monitoring form and training of key staff
Sources of Information (All available from SERVE upon request)
Result 2.1: KPI 1: SERVE reporting templates (completed during volunteering programme & monitoring visits); KPI 2: Tapologo beneficiary numbers per centre, updated monthly.
Result 2.2: Comprehensive questionnaires completed by partners with beneficiaries in Nov/Dec 2013 (follow up). Questionnaires focus on knowledge, actions and intentions related to ABC issues. Robust Excel based scoring system complements questionnaires

## TVET
SERVE SDP 2012-15 Results Framework
Programme: SERVE Development Programme
Time Period: 2012-2016
Geographic Focus: South Africa, Mozambique & Zimbabwe
Overall Goal: Reduce vulnerability and improve livelihood security for poor children, young people, women and men in targeted communities in RSA, Moz & Zim
Outcome 3: Improved employment and self-employment prospects for young adults in targeted communities
Objectives: (5) Increase access to non-agricultural effective TVET opportunities with emphasis on poorest and most marginalised
(6) Launch agricultural based TVET training programmes based on Franchise model at Dondo, Mozambique
Result | Target Beneficiaries | Key Performance Indicators | Baseline | Target 2012 | Results 2012 | Target 2013 | Results 2013 | Target 2014 | Results 2014 | Target 2015 | Results 2015 | Target 2016
3.1 Graduates of Tsholofelo Community TVET Programme have increased individual income (each year) | 170 young people and adults (average age of 30) living in squatter camps in Rustenburg, RSA. 70% female, 30% male | 1. Average of Pre/Post course individual income of graduates, measured at 6 month intervals | 2012 Baseline: individual income of €45 per month (Nov, 2011) 2013 Baseline: Individual income of €52 per month (Feb, 2013) 2014 Baseline: Individual income of €51 per month (Q2 2014) 2015 Baseline: Individual income of €43 per month (Q1 2015) 2016 Baseline: €39 per month (Q1 2016) | 1. Original indicator changed | 1. 24% increase in average post course individual income of graduates to €56 a month (Nov 2012) | 1. 25% increase in average post course individual income of graduates to €65 a month | 1. 15% increase in average post course individual income of graduates to €60 per month (Dec 2013) - OFF TRACK (SLIGHTLY) 29% male, 71% female, average age 30 | 1. 25% increase in average post course individual income of graduates | 1. 24% increase in average income of graduates to €63 a month - ON TRACK 325 benefic. (20% male, 80% female) 15-24 years - 5%; 25-34 years - 27%; 35-44 years - 45%; 45+ yrs - 22% | 1. 25% increase in average post course individual income of graduates | 1. 51% increase on annual baseline in average income of graduates to €65 a month - ON TRACK | 1. 25% increase in average post course individual income of graduates
3.2 Young Africa Zimbabwe TVET Centre at Epworth increases throughput on effective TVET courses by 130% by 2016 (Effective refers to TVET programme leading to increased individual income for graduates) | 600 young people each year (15-25 years) with poor education and employment prospects living in the Epworth community, Zimbabwe and who enrol on TVET programmes (129 female, 211 male) | 1. Completion of construction work by 2014 2. % change in centre throughput post construction work 3. Pre/post TVET course individual income, measured at 6 month intervals | 1. No new construction work started 2. Current capacity is 300 young people (198 female, 102 male) 3. 2014 Baseline: Average individual income of $180 per month 2015 Baseline: Average individual income of $70 per month 2016 Baseline: $15 a month | Complete Phase 1 of Construction | Phase 1 Construction underway - on track | Complete Phase 2 of Construction | 1. All construction work completed by January 2014 - ON TRACK Centre will open for new students from February 2014 onwards, when the results to KPIs 2 & 3 will become available 63% male, 37% female, 86% aged 15-19, 14% aged 20+ | (ii) 65% throughput increase (iii) Income: 15% increase on 2014 baseline to $207 per month | (ii) 97% throughout increase - 590 young people benefitted in 2014 - ON TRACK (iii) No income increase amongst 2014 graduates (OFF TRACK) 36% male, 64% female (33% aged 17-19; 50% aged 20-24; 17% aged 25 yrs+) | (ii) 130% throughput increase (iii) 15% increase on 2015 baseline (adj) See Note 3, 2014 | (ii) 156% throughout increase - 768 young people benefitted in 2015 - ON TRACK (62% female, 38% male) (iii) Post course average monthly income of $112, (60% increase) - ON TRACK 12% male, 88% female (17-20 yrs: 56%; 21-25 yrs: 32%; 26 years +: 12%) | (ii) 156% throughput increase (iii) 25% increase on 2016 baseline when it becomes available
3.3 At least 80% of new micro credit loans to TVET Franchisees and graduates being repaid by 2016 | (i) TVET students (60% female, 40% male) at YA Zimbabwe who complete business training programmes such as Junior Achievement Zimbabwe, Start Your Own Business by ILO (ii) 50 graduates (45% female, 55% male) & 10 franchiseees (33% female, 66% male) at YA TVET Centre, Beira, Mozambique (iii) 50 graduates (40% female, 60% male) & 10 franchisees (33% female, 66% male) at YA Agri Tech Centre, Dondo, Mozambique | 1. Repayment rate of micro credit loans, measured quarterly | 1. 71% of micro credit loans being repaid at YA Zimbabwe (2011) 2. 47% repayment rate at YA Mozambique (2010) 3. YA Agri Tech is a new project and is currently in it's first term of enrolled students | 1. 75% repayment rate of micro credit loans at YA Zim 2. 65% repayment rate of micro credit loans at YA Beira 3. N/A - start up phase at YA Dondo | 1. 43% repayment rate of loans at YA Zim - off track 2. 24% repayment rate of loans at YA Beira - off track 3. N/A until 2014 | 1. 60% repayment rate of micro credit loans at YA Zim 2. 70% repayment rate of micro credit loans at YA Beira 3. N/A - rollout of first courses | 1. Overall, 61% repayment rate of all loans disbursed at YA Zim (2012: 37%, 2013: 80%) - ON TRACK 2. Overall, 52% repayment rate for all loans disbursed at YA Moz in 2012 & 2013 - OFF TRACK 3. Information will be available in 2014 Moz: 52% male, 48% female Zim: 34% male, 66% female, 20% below 20 years, 60% aged 20 - 25, 20% above 25 years | 1. 70% repayment rate of micro credit loans at YA Zim 2. 65% repayment rate of micro credit loans at YA Beira 3. 70% repayment rate of micro credit loans at YA Dondo | 1. 55% repayment rate of micro credit loans at YA Zim - OFF TRACK 2. 69% repayment rate on micro credit loans at YA Beira (ON TRACK) 3. No micro credit disbursed in 2014 - OFF TRACK See Note 4, 2014 Moz: 55% male, 45% female Zim: 39% male, 61% female | 1. 70% repayment rate of micro credit loans at YA Zim (adj) 2. 70% repayment rate of micro credit loans at YA Beira (adj) 3. 50% repayment rate of micro credit loans at YA Dondo (adj) | 1. 60% repayment rate of micro credit loans at YA Zimbabwe - OFF TRACK 2. 72% repayment rate of loans at YA Beira - ON TRACK 3. TBC Moz: 51% female, 49% male Zim: 39% male, 61% female | 1. 60% repayment rate of loans at YA Zim; 2. 80% repayment rate of micro credit loans at YA Beira 3. 80% repayment rate of micro credit loans at YA Dondo
3.4 Young Africa Agri Tech Programme delivers effective agriculture focused TVET training to 1000 rural youth and 300 farmers by 2016 (Effective refers to TVET programme leading to increased individual income for graduates) | (i) 1000-1500 rural youth (15-24 year olds, over a 4 year period) from Beira corridor communities of Mozambique (33% female, 66% male) (ii) 300 farmers (50% female, 50% male), over a 4 year period from Beira corridor communities in Mozambique | 1. Completion of Phase 1, Phase 2 & Phase 3 construction work by end of 2015 2. Pre/post course individual income rates of graduates, measured at 6 month intervals 3. Self sustainability of TVET Centre, measured annually | 1. Currently greenfield site 2. Secondary data: Beira Agricultural Growth Corridor Report states that for rural households in this area "average income per capita is less than $300" Primary baseline (2014) is $47 per student per month (Family income is $143 per month) 2015 Baseline: 2335Mt - $65 2016 Baseline: 1,116Mt 3. New project - no baseline available | 1. Phase 1 50% complete 2. No graduates during construction phase 3. Not applicable in construction phase | 1. Phase 1 50% complete - on track 2. N/A until 2014 3. N/A until 2014 | 1. Phase 1 100% complete 2. No graduates - first year of courses 3. Not applicable in construction phase | 1. Phase 1 is 100% complete - ON TRACK First tranche of beneficiaries will enrol in February 2014 onwards, when baselines for KPI 2 & 3 will become available | 1. Phase 2 100% complete 2. 25% increase in average post course individual income of graduates 3. Start up phase | 1. Phase 2 -80% complete - ON TRACK 2. 13% increase in average post course individual income of graduates to 1800Mt ($53) per month - OFF TRACK 3. Start up phase - n/a 57% male, 43% female Average Age: 23 | 1. Phase 3 100% complete 2. 15% increase in average post course individual income of graduates (adj) - SEE NOTE 5, 2014 3. 25% self sustainability rate | 1. Phase 3 75% complete; 2. 24% increase in average post course individual income of graduates to $81 a month (on track); 3. AT Not yet generating substantial income - (Off Track) | 1. Phase 3 100% complete ; 2. 20% increase in average post course individual income of graduates; (adj) - SEE NOTE 5, 2014 3. 30% self sustainability rate
3.5 Improved sustainability and effectiveness of Franchise Model at Young Africa TVET Centres in Beira, Mozambique by 2016 Sustainability defined as income vs running expenses | 650 - 800 young people (aged 15-24) each year with poor educational and employment prospects from the Manga community and wider Beira communities in Mozambique. Target of 45% female/55% male beneficiaries | 1. Self sustainability level of TVET Centre, measured annually 2. % of agreed rental income from Franchisees achieved at year end 3. Pre/post course average monthly individual income of graduates, measured at 6 month intervals | 1. 55% self sustainability (2011) 2. 85%, Dec 2012 3. $63 per month is a new and more accurate baseline (Jan 2013) 2014 Baseline: Average individual income of $76 per month (May 2014) 2015 Baseline: Average individual income of $80 per month (Feb 2015) 2016 Baseline: TBC | 1. 70% self sustainability 2.(a) Dependent on baseline 3. $90 per month (off track, due to revised baseline figure. Targets for 2013-15 adjusted) | 1. 82% self-sustainability - on track 2. 85% of agreed rents paid 3. $63 is a new and more accurate baseline | 1. 85% self-sustainability (adj) 2. 90% of agreed rents paid (new) 3. $75 per month | 1. 86% self-sustainability - ON TRACK 2. 88% of agreed rents paid - OFF TRACK (Slightly) 3. $82 per month (30% increase) - ON TRACK 55% male, 45% female; 20% aged 16-19, 43% aged 20-25, 37% aged 26+ | 1. 90% self-sustainability 2. 95% of agreed rents paid 3. $95 per month (25% increase on 2014 baseline) | 1. 90% self-sustainability (ON TRACK) 2. 70% of agreed rents paid (OFF TRACK) 3. $109 per month (43% increase) - ON TRACK 53% male, 47% female; 38% aged 16-19, 41% aged 20-25, 21% aged 26+ | 1. 100% self-sustainability 2. 100% of agreed rents paid 3. $100 per month (25% increase on 2015 baseline) | 1. 100% self-sustainability (TBC) 2. 72% of agreed rents paid (Off Track) 3. $119 per month (49% increase on 2015 baseline) 51% male, 49% female; 20-25 years: 56%. 26-30 years: 20%; 30 years +: 24% | 1. 100% self-sustainability 2. 85% of agreed rents paid (adj) 3. 25% increase on 2016 baseline (finalised in Q1 2016) See Note 3
3.6. Graduates from Young Africa Zimbabwe's Mobile Vocational Skills Training Programmes have increased incomes by 2016 | 2014: 125 young people (aged 15-24) per year with poor educational and employment prospects from the rural Domboshava community Zimbabwe. Target of 50% female/male beneficiaries 2015: 130 young people (aged 15-24) per year with poor educational and emploument prospects from the rural area of Chipinge District, Manicaland. Target of 50% female/male beneficiaries | 1. Pre/post course average monthly individual income of graduates, measured at 6 month intervals | 2014 Baseline: Average individual income of $93 per month (May 2014) 62% Female/38% Male; 36% aged 17-20, 33% aged 21-25, 30% aged 25-35 2015 Baseline: Average individual income of $33 per month (August 2015) 63% male/37% female; 42% aged 15-20 yrs, 30% aged 21-25 yrs, 28% aged 25 yrs + 2016 Baseline: Average individual income of $37 per month (March 2016) 61% male/39% female; 43% aged 15-20; 30% aged 21-25; 27% aged 26+ | N/A - project begins Q2 2014 | N/A - project begins Q2 2014 | N/A - project begins Q2 2014 | N/A - project begins Q2 2014 | 20% increase in average monthly individual income to $112 | 20% increase in average monthly individual income to $112 (ON TRACK) (65% female, 35% male Age - 17-19 yrs: 24%, 20-24 yrs: 34%, 25 yrs +: 39%) | 20% increase in average monthly individual income based on 2015 baseline (available April/May 2015) | 1. Post course average monthly income of $69 (54% male, 46% female 15-20 yrs: 44%; 21-25 yrs: 40%; 26 years +: 16%) | 20% increase in average monthly individual income based on 2016 baseline
Key Programme Outputs 2012-2016
Target 3.1 At least 70 young people each year graduating from Tsholofelo Community TVET Programme in Rustenburg, RSA
2012 Result 3.1: Inclusion of ABET into Community TVET Programme meant that 161 people (77% female/23% male) graduated in 2012, although age group was older than predicted - off track in terms of target group
2013 Result 3.1: Waiting on information from Tsholofelo
2014 Results 3.1: 325 people enroled in 2014 and 216 graduated - 66% graduation rate - ON TRACK
2015 Result 3.1:389 people enroled in 2015 and 232 graduated - 60% graduation rate (approx 100 have exams in February 2016) - ON TRACK
Target 3.2 Large extension to YA Zimbabwe Epworth TVET Centre completed
2012 Result 3.2. Construction work underway and expected to be completed by July 2013 - on track.
2013 Result 3.2: Construction work completed in January 2014, first students enrolled for February 2014 - on track
2014 Results 3.2: First courses run from new workshops at Epworth started in February 2014 - ON TRACK
Target 3.3 Approximately 150 young people/franchise holders receive micro credit support over programme period in Mozambique & Zimbabwe
2012 Result 3.3: 24 young people recieved loans in 2012 (15 at YA Zimbabwe - 46% male/54% female, 9 at YA Mozambique - 11% female, 89% male). 37% below annual target of 38 youth but can be made up in future years - off track
2013 Result 3.3: 54 young people received loans in 2013 (29 at YA Zimbabwe, 25 at YA Mozambique - 60% female, 40% male).
2014 Results 3.2:15 recipients at YA Mozambique in 2014 - 55% female, 45% male. No new recipients at YA Zimbabwe in 2014 - between 2012 & 2014 a total of 45 young people received loans (62% female, 38% male)
2015 Result 3.3: 32 recipients at YA Mozambique in 2015 - 56% male, 44% female. No new recipients at YA Zimbabwe in 2015 - between 2012 & 2014 a total of 45 young people received loans (62% female, 38% male)
Target 3.4 Construction phases and instalment of utility services completed at Young Africa Agri Tech Centre, Dondo, Mozambique
2012 Result 3.4: Large scale infrastructure development underway, supported by number of donors including EU & USAID - on track
2013 Result 3.4: All utilities installed at YA Agri Tech, construction phases on track. First students will be enrolled in February 2014 - on track
2014 Results 3.4: All construction work & utility services on track, except for Food Processing Components. First courses run in 2014 - on track
2015 Result 3.4: All construction work & utility services on track, except for Food Processing Components. First courses run in 2014 - on track
Target 3.5 Training equipment upgraded at TVET Centres in Beira and Dondo, Mozambique benefitting between 1,250 and 1.750 young people per annum plus 300 older farmers
2012 Result 3.5: Training equipment being upgraded incrementally at Beira and Dondo. Access to micro credit funding in 2013 for franchise holders will lead to further improvements - on track
2013 Result 3.5: Training equipment being upgraded at YA Beira. 8 Franchise Holders took micro-credit loans which are being used for investing in equipment. 60% repayment rate suggests loans performing and being well used - on track
2014 Results 3.5: Training equipment upgraded at YA Beira. 3 Franchise Holders took micro-credit loans used to invest in equipment. 2,200 beneficiaries in 2014 across both sites - on track
2015 Result 3.5: Training equipment upgraded at YA Beira. 5 Franchise Holders (4 male, 1 female) took micro-credit loans used to invest in equipmen - on track
Target 3.5 Successful recruitment of an Entrepreneurship Promoter to build Business Training Capacity of students and Franchise Holders
2012 Result 3.5: Entrepreneurship Promoter recruited and resourced, working with Franchise Holders and students at YA Beira & Agri Tech - on track
2013 Result 3.5: Entrepreneurship Promoter working with Franchise Holders and Students, focusing on microcredit and market linkages - on track
2014 Results 3.5: New Entrepreneurship Promoter worked with Franchise Holders and Students, focusing on microcredit, capacity building & market linkages - on track
2015 Result 3.5: EP worked with Franchise Holders and students - focused on microcredit, capacity building & market linkages - on track
Target 3.6 Graduates from Young Africa Zimbabwe's Mobile Vocational Skills Training Programme have increased incomes by 2015
2014 Results 3.6: 194 people enrolled in Outreach Programme, 170 graduated - 88% graduation rate. Increase in incomes reported. - On Track
2015 Result 3.6: 246 young people graduated from the Chipinge Outreach Training Programme in 2016 - On Track
Underlying Assumptions/Contingencies
Result 3.1: Working with people in squatter camps, who are often the most marginalised and poorest, sometimes yields results that are less favourable than other groups and TVET models/ Attention to lesson learning from evaluations
along with studying alternative YA TVET model and opportunities for replication. At least 50% of graduates giving financial information during monitoring process
Result 3.2: Funding for large construction project can be secured from a range of sources/ Diversified funding strategy developed which is targeting other donors
Result 3.3: Risk of fraud with allocation of micro credit/ Strengthened assessment of micro credit process involving programme officer, marketing officer, Director and Board of Trustees
Result 3.4: Funding for large construction projects can be secured from a range of sources/ Diversified funding strategy developed which is targeting other donors
Result 3.5: Franchise holders reluctant to provide financial information to gauge profit levels/ Offer business development support and access to micro credit managed by Entrepreneurship Promoter
Sources of Information (All available from SERVE upon request)
Result 3.1: Pre course & post course questionnaires completed with beneficiaries from June 2012 onwards. Focused on income levels & sources, education, employment, use of skills and future plans.
Result 3.2: KPI 1: Quarterly reports from Young Africa Zimbabwe & monitoring visits undertaken by SERVE Long Term Volunteer. When appropriate, sources for KPI 2 & KPI 3 will include partner records & income questionnaires
Result 3.3: Micro credit tracking system that is in place at YA Zimbabwe & YA Mozambique. This system is robust and has been in use for sometime. Results forwarded to SERVE quarterly
Result 3.4: KPI 1: SERVE reporting templates, completed during volunteering programme & monitoring visits by SERVE staff and long term volunteer. When appropriate, sources for KPI 2 & KPI 3 will include
income questionnaires and YA annual accounts
Result 3.5: For KPI 1 & 2, Young Africa accounts (to compare income vs running expenses). For KPI 3, Pre course & post course questionnaires completed with beneficiaries from June 2012 onwards.
Focused on income levels & sources, education, employment, use of skills & future plans

## Capacity Building
SERVE SDP 2012-15 Results Framework
Programme: SERVE Development Programme
Time Period: 2012-2016
Geographic Focus: South Africa, Mozambique & Zimbabwe
Overall Goal: Reduce vulnerability and improve livelihood security for poor children, young people, women and men in targeted communities in RSA, Moz & Zim
Outcome: Contribution to Outcomes 1, 2 & 3
Objective 3: To strengthen capacity of SERVE and partners to implement best practice, plan strategically, strengthen governance, advocate and mobilise local communities
Result | Target Beneficiaries | Key Performance Indicators | Baseline | Target 2012 | Results 2012 | Target 2013 | Results 2013 | Target 2014 | Results 2014 | Target 2015 | Results 2015 | Target 2016
4.1 Improved governance structures that drive enhanced programme quality and programme impact and strengthens relationships with key donors/ stakeholders | 1. SERVE and the 4 Strategic partners in the Programme Area 2. Boards of each of the 4 Strategic Partners and the respective staff and beneficiaries 3. Personnel working on results based management process | 1. Preparation of Governance manuals for each programme partner organisation 2. Formal board reviews using Dochas Code of Corporate Governance 3. Number of key donors supporting SERVE and programme partners | 1. SERVE and Tapologo have documented governance polices while none of the partners have documented governance manuals 2. Board reviews are currently informal and not structured 3. 5 Key donors | 1. SERVE & Tapologo to complete Governance manuals 2. No Board reviews planned 3. 5 key donors | 1. SERVE Governance Manual will be completed by March 2013 Tapologo manual expected to be completed May 2013 2. N/A 3. 5 key donors - on track | 1. Young Africa in Moz and Zim to complete Governance manuals 2. SERVE & Tapologo complete formal board reviews 3. 6 key donors | 1. The SERVE Governance Manual was completed in Q4 2013, but was not replicated with any partners - OFF TRACK (Slightly) 2. No formal board reviews completed in 2013 - OFF TRACK 3. 10 key donors (excluding SERVE/Irish Aid) - ON TRACK | 1. Tsholofelo & Tapologo complete Governance manual (adj) 2. Tapologo & Tsholofelo complete formal board reviews (adj) 3. 11 key donors (adj) | 1. Governance Manual not rolled out with partners in 2014 - OFF TRACK; 2. Board Reviews not completed in 2014 - OFF TRACK; 3. 12 key donors (excluding SDP funds) - ON TRACK | 1. Tsholofelo & Tapologo complete Governance manual (adj) 2. Tapologo & Tsholofelo complete formal board reviews (adj) 3. 12 key donors | 1. New governance structure & constitution at Tsholofelo. YA have started process of clarifying governance issues between HQ and Centre Level (On Track) 2. Review completed with Tsholofelo as part of governance changes (On Track) 3. 17 key donors amongst partner organisations (On Track) | 1. Governance structures clarified at YA 2. YA Moz & YA Zimbabwe complete formal board reviews (adj) 3. 17 key donors
4.2 The programme partners deliver cost-effective infrastructure and service outcomes while increasing the percentage volunteer contribution of the partners workforce | 1. 150 Irish volunteers acting as catalysts to engage increased voluntary engagement in the target overseas communities 2. Potential future leaders and activists emerging from the voluntary sector in the target communities | 1. The total economic value of the combined international and local voluntary contribution 2. The % of the partner workforce contributed by volunteers 3. The number of local community volunteers on the boards of the programme partners | 1. In 2011, for the four programme partners 83,200 hours by €3.50 = €291,200 2. (a) YA Zim- 15% (b) YA Moz - 20% (c) Tapologo - 25% (d) Tsholofelo - 12% Secondary Data - Worldwide for non-profit 44% (Johns Hopkins) 3. 4 local community volunteers | 1. €300,000 2. Average of 22% 3. 6 local community volunteers | 1. Efforts to quantify value of volunteering contribution were unsuccessful in 2012. This will be reviewed with partners in March 2013 2. Average of 29% - on track (a) YA Zim - 9% (b) YA Moz - 23% (c) Tapologo - 69% (HBCG) (d) Tsholofelo - 15% 3. 8 community volunteers on Boards of Partners - on track | 1. €325,000 2. Average of 27% 3. 8 local community volunteers | 1. €117,600 - OFF TRACK 2. Average of 19% - OFF TRACK (a) YA Zim - 10% (b) YA Moz - 33% (c) Tapologo - 3% (d) Tsholofelo - 28% 3. 10 community volunteers on Management Boards of partners (YA Zim - 4, YA Moz - 4, Tapologo - 1, Tsholofelo - 1) - ON TRACK | 1. €120,000 (adj) 2. Average of 25% (adj) 3. 12 local community volunteers (adj) | 1. €114,715 - OFF TRACK (Slightly) 2. Average of 14% - OFF TRACK (a) YA Zim - 11% (b) YA Moz - 26% (c) Tapologo - 7% (d) Tsholofelo - 30% 3. 15 community members on Management Boards of partners (YA Zim - 4, YA Moz - 5, Tsholofelo - 4, Tapologo - 2) - ON TRACK | 1. €120,000 (adj) 2. Average of 20% (adj) 3. 15 local community volunteers (adj) See Note 6, 2014 | 1. €146,000 2. Average of 18% across 4 SDP partners 3. 13 local community volunteers | 1. €80,000 (adj) 2. Average of 20%; 3. 13 local community volunteers (adj) See Note 4
4.3 The programme by building the capacity of the voluntary sector contributes directly to the achievement in the target communities of increased social capital, social cohesion, personal development and empowerment (all "immeasurable impacts") | 1. Partner peer staff, community leaders, creche teachers, local teachers, local youth leaders, community activists 2. Marginalised and disadvantaged "difficult to work with" young people 3. Participants in community initiatives led by the volunteer to build capacity programme | 1. The increase in the number of active youth parliaments in the target communities 2. Examples of breaking the cycle of disadvantage - Telling the stories of transformed lives 3. Examples of Community Campaigns and the change achieved | 1. 2 active youth parliaments at YA Beira and YA Zimbabwe 2. Evidence of breaking the following repeated cycles of disadvantage in specific contexts: - Reducing violence and anti-social behaviour in two squatter camps in South Africa- (Crime rates); - Lives changed through first generation opportunity to agriculture TVET training in Sofala Region of Mozambique (There are currently no opportunities) - From subsistence agriculture to commercial agriculture (96% in Sofala region) - Whats it like when a community can look after its own vulnerable children (4 communities in South Africa) - Girls engaged in TVET- learning skills traditionally the preserve of men in Moz 3. We start from a zero base and explore the impact of community campaigns led by volunteers | 1. 3 youth parliaments (YA Epworth initiated) 2. Reduced violence in squatter camps (Telling the story) 3. Squatter campaign that achieves change | 1. 2 active parliaments - new YA Epworth parliament will be initiated in Q3 2013 (off track); 2. Role of employment and accessible TVET in reducing violence and anti-social behaviour explored in written form, available on SERVE website and disseminated to past volunteers and partners; (on track); 3. SERVE is currently preparing a case study on the impact of a community campaign focused on ABET in the community of Mbekisan in Rustenburg, RSA. This will be finalised by Q1 2013 - off track | 1. 4 youth parliaments (YA Dondo initiated) 2. OVCs at home in their own communites (Telling the story) 3. Young people's voluntary campaigns that achieve change | 1. 3 youth parliaments active - YA Beira (Moz), YA Chitungwiza (Zim) & YA Epworth (Zim). Voice of young students formally contributing to development process - OFF TRACK (Slightly) 2. OVC story not completed in 2013 - instead a video case study is being planned for June 2014 - OFF TRACK 3. SERVE provided funding and training (youth leadership, proposal writing) to help with the establishment of a new youth group (called Step Up and Serve) associated with our partner Tsholofelo in South Africa. This is a voluntary group committed to working with vulnerable young people living in squatter camps in the Rustenburg area. Their main aim is to encourage young people to make good life choices and assume responsibility for development issues within their own community - based on "Meitheal" model run in Irish schools - ON TRACK See Note 11 | 1. 4 youth parliaments (Tsholofelo initiated) 2. First generation Agriculture TVET openings in Sofala region of Moz (Telling the story) 3. Continue to support Step Up and Serve group and document impact of their voluntary work (adj) | 1. 4 youth parliaments active - YA Beira, YA Chitungwiza, YA Epworth & Tsholofelo (On Track); 2. Story of Agri Tech captured in video form, and disseminated through SERVE website; 3. SERVE provided funding support to the Step Up and Serve group in 2014, who played a key role during two Serve volunteer programmes in 2014 | 1. 5 youth parliaments 2. From subsistence to commercial farming- women at the centre (Telling the story) 3. Evidence that OVCs are contributing to their communities in a voluntary capacity | 1. 5 youth parliaments active - YA Beira, YA Dondo, YA Chitungwiza, YA Epworth & Tsholofelo (On Track); 2. Case study completed on female graduates from YA Agri Tech Programme, disseminated through SERVE website (On Track); 3. SERVE provided technical and funding support to the Step Up and Serve group in 2015. They plated a key role during SERVE Volunteer Programmes and engaged in community activities in 2015 (On Track) | 1. 5 youth parliaments; 2. Case study on YA TVET Programme Graduates disseminated through SERVE network; 3. Continue to support Step Up and Serve group and document impact of their voluntary work
Programme Outputs 2012-2016
Target 4.1 Volunteer to Build Capacity Programme recruits, trains and assigns approx 40 volunteers annually to programme partners and acts as a catalyst for engaging 500 volunteers annually in target communities
2012 Result 4.1: 29 volunteers placed in programme countries in 2012 - 30% below target. SERVE volunteers act as a catalyst for local communities - see "The Impact of Volunteering on the Development Process" on www.serve.ie/sdp
Political climate in Zimbabwe makes it unsuitable to host group volunteering programmes at present
2013 Result 4.1: 47 volunteers placed in programme countries in 2013, acting as catalyst for local communities - ON TRACK
2014 Result 4.1: 38 volunteers placed in programme countries in 2014, acting as a catalyst for local communities - ON TRACK
2015 Result 4.1: 23 volunteers placed in programme countries in 2015, acting as a catalyst for local communities - ON TRACK
Target 4.2. Strengthened Governance and Management for Results and Monitoring and Evaluation systems achieved leading to improved lesson learning, resource allocation and programme impact
2012 Result 4.2: Improved M & E Systems amongst programme partners allowing for collection of data to track SDP - on track
2013 Result 4.2: M & E and RBM systems embedded within organisations, providing good data for tracking SDP. Learning from data will form part of narrative report - ON TRACK
2014 Result 4.2: M & E and RBM systems embedded within organisations, providing good data for tracking SDP. Learning from data will form part of narrative report - ON TRACK
2015 Result 4.2: M & E and RBM systems embedded within organisations, providing good data for tracking SDP. Significant progress made in 2015 by RBM Training Course - ON TRACK
Target 4.3 Enhanced social capital and social cohesion in target communities
2012 & 2013 Result 4.3: Although difficult to measure, anecdotal evidence and discussions with partners helps to boost social capital and cohesion in target communities - see www.serve.ie/public-engagement-campaigns/
& http://www.serve.ie/diaries-and-photos/
2014 Result 4.3: Anecdotal evidence and discussions with partners helps to boost social capital and cohesion in target communities - see http://www.serve.ie/category/blog
Underlying Assumptions/Contingencies
Result 4.1: The necessary social, technical and management skills as well as adequate financial and technological resources are available/ The Dochas code will be applied but the emphasis will be about getting the basic things right,
making sure that all concerned are working together to a common cause.
Result 4.2: The interest in volunteering by an appropriate skills based volunteering pool remains strong and that partners continue their commitment to developing the voluntary sector/ Expanded range of volunteering options are
developed to include short-term, long-term, solidarity programmes, immersion and cross-partner volunteering with refocused strategy for engaging local communties.
Result 4.3: The value of the voluntary sector should be seen in more than simply economic terms/ The economic value of volunteering must be taken with other measurement tools on social capital, social cohesion, personal development
and empowerment. The programme will pay attention to the research work underway to create common metrics for systematically and continuously measuring the economic value of volunteering.
Sources of Information (All available from SERVE upon request)
Result 4.1: KPI 1: Minutes of SERVE Board meetings; KPI 3: Correspondence with partners & review of programme budgets which outline all donors contributing to programmes
Result 4.2: KPI 1 & KPI 2: Template to monitor voluntary contribution at partners, based on number of volunteers, type of volunteer, number of hours donated;

## Public Engagement
SERVE SDP 2012-15 Results Framework
Programme: SERVE Development Programme
Time Period: 2012-2016
Geographic Focus: Ireland
Overall Goal: Reduce vulnerability and improve livelihood security for poor children, young people, women and men in targeted communities in RSA, Moz & Zim
Outcome: Increased awareness that leads to active participation amongst a targeted constituency in supporting development initiatives pivotal to reducing vulnerability and enhancing livelihood security
Objectives: (a) To increase awareness of development education and Ireland's role in addressing poverty and inequality
(b) To help empower targeted groups to actively participate with networks and campaigns committed to building a constituency for change in favour of the developing world
Result | Target Beneficiaries | Key Performance Indicators | Baseline | Target 2012 | Results 2012 | Target 2013 | Results 2013 | Target 2014 | Results 2014 | Target 2015 | Results 2015 | Target 2016
5.1 Target group of 400 volunteers benefitting from SERVE development education programme with at least 50% actively involved in initiatives in support of international development | 1. 150 volunteers (50% male, 50% female) who will be assigned to the SDP Programme partners 2. 250 volunteers (50% male/50% female) who will be assigned to 7 other partners 3. Family, friends, peers of volunteers as well as development sector stakeholders | 1. % of volunteers rating dev ed programme as "beneficial" 2. Impact of dev ed programme on volunteers one year after placement - focusing on awareness levels, critical thinking on development issues and active citizenship 3. % of returned volunteers active in Solidarity Groups or Change Groups, measured annually 4. % of returned volunteers contributing financially to Development NGO's (excluding fundraising as part of SERVE Volunteer Programme) | 1. 66% of volunteers rated development education training as "beneficial" (2011) 2. > Awareness - on a scale of 1-10 across 7 development issues the average was 4.54 - 45% before placement; > Critical Thinking - 75% think critically as a result of SERVE DEP > Active Citizenship - 63% actively involved in campaigns and speaking formally about experiences 3. Approximately 7% of volunteers (70% female, 30% male) active in SERVE Solidarity Groups in 5 locations/ (Baseline will be developed for other Change Groups) 4. 30% contribute financially regularly (2011) | 1. 75% of vols rate dev ed programme as "beneficial" 2. N/A - baseline set in Q3 2012 3. 10% participation rate (60% female, 40% male) 4. 35% | 1. 91% of volunteers (57% female, 43% male) rated development education programme as "beneficial" or "very beneficial" - on track; 2. > Awareness - 7.37 (73%) on a scale of 1 to 10 across 7 development issues; > Critical Thinking - 75% think critically > Active Citizenship - 63% actively involved in campaigns and speaking formally about experiences 3. 8% participation rate (60% female) amongst past volunteers - off track {20% participation rate amongst 2012 volunteers} 4. 20% of 2012 returned volunteers contributing financially to development NGOs - off track | 1. 90% of vols rate dev ed programme as "beneficial" 2. > Awareness (post placement) - 7.50 > Critical Thinking - 75% > Active Citizenship - 65% 3. 10% participation rate (50% female, 50% male) 4. 40% | 1. 69% of SERVE Volunteers rates the dev ed programme as "beneficial" or "very beneficial" - OFF TRACK 2. > Awareness (post placement) - 6.75 > Critical Thinking - 81% think critically > Active Citizenship - 48% are active in speaking about their experience & campaigns - OFF TRACK 3. 15% participation rate (60% female, 40% male) - ON TRACK 4. 47% of returned SERVE volunteers contributing financially to development NGOs - ON TRACK | 1. 80% of vols rate dev ed programme as "beneficial" (adj) 2. > Awareness (post placement) - 7.50 > Critical Thinking - 80% > Active Citizenship - 70% 3. 15% participation rate (60% female, 40% male) (adj) 4. 50% (adj) | 1. 92% of SERVE Volunteers rated the DEP "beneficial" or "very beneficial" - ON TRACK 2. Awareness (PP) - 6.72 (KAP) - 8.04 > Critical Thinking - (PP) - 37% (KAP) - 84% > Active Citizenship - (PP) - 53% (KAP) - 46% Overall, OFF TRACK 3. Just 1 Solidarity Group active at present, OFF TRACK 4. PP - 56% KAP - 59% ON TRACK SEE NOTE 7, 2014 PP = post placement evaluation with 2014 volunteers only KAP = knowledge, attitudes, practice survey with 2003-2014 volunteers | 1. 90% of vols rate dev ed programme as "beneficial" 2. > Awareness (post placement) - 7.00 > Critical Thinking - 80% > Active Citizenship - 50% (adj) 3. 20% participation rate (60% female, 40% male) (adj) 4. 55% | 1. 89% of volunteers rate dev ed programme as "beneficial" (On Track) 2. Awareness (PP) - average of 7.70 across 12 development issues > Critical Thinking - 73% > Active Citizenship - 34% Overall, Off Track 3. 34% participate in international NGO activity post placement (On Track) 4. 67% (On Track) Average Age of Volunteers: 24 Gender Profile: 70% female, 30% male | 1. 90% of vols rate DEP as "beneficial"; 2. Awareness (post placement) - 7.50; > Critical Thinking - 80% > Active Citizenship - 50% (adj); 3. 35% participation rate (60% female, 40% male); 4. 67%
5.2 Contribution to a momentum and movement for change in favour of the MDGS relevant to HIV/AIDS, OVC's and TVET and the role of the voluntary sector in the development process | 1. SERVE's 4 Strategic Partners and the beneficiaries that they serve 2. Returned volunteers and other targeted invitees 3. Irish Government, EU, Politicians, UN and other power brokers 4. Other alliance and networks and campaigning groups - specifically Comhlamh, Dochas, Coalition of Aid and Development Agencies Northern Ireland (CADA NI), Centre for Global Education & Global Education Network Northern Ireland (GENNI) | 1. Four Advocacy initiatives completed (one initiative per calendar year); 2. Level of engagement of 120 SERVE volunteers and wider estimated target audience (see Footnote 1) 3. Progress in areas of HIV/AIDS, OVC & TVET reported in annual MDG reports (see Footnote 2) 4. Response of alliance and network groups to case studies of SERVE volunteer's and partner volunteer's impact on the development process. Focus on perceptions of volunteering, social inclusion, contribution, impact & sustainability. | 1. No Advocacy initiatives active at present 2. Active engagement of 120 SERVE volunteers and an estimated target audience of 12,000 people each year 3. New initiative - no existing strategy of mainstreaming MDG agenda into SERVE network 4. No existing formal case study | 1. Advocacy initiative on HIV/AIDS/ and the MDGs 2. Engagement of 30 volunteers & 12,000 people 3. Mainstream MDG progress (in areas relevant to SDP) to SERVE network; 4. Completion of one case study with learning disseminated to important stakeholders | 1. Campaign on HIV/AIDS implemented. Focused on awareness raising amongst volunteers & young people - beneficiaries reported a 65% increase in knowledge; 2. 28 volunteers and approximately 6000 people; 3. SERVE e-newsletter, "Focus On" will discuss MDG 2012 Report as relevant to the SDP; 4. Case study on "Impact of Volunteering on the Development Process" completed. Published on SERVE website and disseminated to stakeholders - on track | 1. Advocacy initiative on TVET/ and the MDGs including (a) Contribution to post 2015 agenda through 500 people in SERVE network adding TVET as a standalone priority issue on UN "My World 2015"campaign; and (b) TVET seminar in Ireland involving NGOs and public; 2. Engagement of 30 volunteers and 6,000 people 3. Mainstream MDG progress (in areas relevant to SDP) to SERVE network; 4. Completion of one case study. To be disseminated to target groups and response noted | 1.(a) 65 people (6% of Irish respondents) in the SERVE network added TVET as standalone issue on UN "My World 2015" campaign and voted for "Better job opportunities" - ON TRACK; 1.(b) TVET seminar held in April 2013. Focus on engaging young people in TVET. Attended by IA and 50 members of the public - ON TRACK; 2. Direct active engagement of 105 past volunteers in TVET advocacy campaigns in 2014. It was not possible to measure wider target audience; 3. Special addition of SERVE Focus On e-magazine dedicated to MDGs most relevant to SDP work. Sent to 780 people in SERVE network - ON TRACK; 4. Case study on micro credit recipients at YA Mozambique completed. Strategy paper on engaging people living in squatter camps in TVET completed - ON TRACK | 1. Advocacy initiative on Voluntary Sector Involvement in Development/ and the MDGs 2. Engagement of 30 volunteers and 6,000 people 3. Mainstream MDG progress (in areas relevant to SDP) to SERVE network; 4. Completion of one case study. To be disseminated to target groups and response noted | 1. Advocacy initiative was not carried out in 2014 (OFF TRACK) 2. Advocacy initiative was not carried out in 2014 (OFF TRACK) 3. Special addition of SERVE Focus On e-magazine dedicated to MDGs most relevant to SDP work. Sent to 800+ people in SERVE network and disseminated on website (ON TRACK) 4. No case study completed during 2014 (OFF TRACK) | 1. Advocacy initiative on OVC/ and the MDGs 2. Engagement of 30 volunteers and 6,000 people 3. Mainstream MDG progress (in areas relevant to SDP) to SERVE network; 4. Completion of one case study. To be disseminated to target groups and response noted | 1 & 2. No SERVE led advocacy initiative. Focus has been on supporting partner led advocacy initatives which are documented in Annual Reports (OFF TRACK); 3. Focus On newsletters on issues of OVC, SDGs & TVET disseminated to SERVE network and read over a thousand times. Read rate is higher than industry averages; (ON TRACK) 4. Case study on YA Zimbabwe Graduate, Giveth Mambo, completed and disseminated through SERVE & Irish NGO network. Featured in Irish Times, shared extensively on social media - see Annual Report for details (ON TRACK) | 1. Engage with Irish Embassy in RSA on an advocacy basis; 2. Engagement of SERVE Volunteers & Network (850 people) in creating awareness of SDGs; 3. Completion of one case study. To be disseminated to target groups and response noted
Programme Outputs 2012-2016
Target 5.1 400 SERVE volunteers complete Development Education training
2012 Result 5.1. In 2012, a total of 120 volunteers completed Dev Ed training (29 of these were in SDP countries) - on track to be achieved over 4 years
2013 Result 5.1: In 2013, a total of 116 volunteers completed Dev Ed Training (47 of these were in SDP countries) - on track to be achieved over 4 years
2014 Result 5.1: In 2014, a total of 105 volunteers completed Dev Ed Training (38 of these were in SDP countries) - on track to be achieved over course of SDP
2015 Result 5.1: In 2015, a total of 60 volunteers completed Dev Ed Training (23 of these were in SDP Countries) - on track
Target 5.2 Organisation of seminar with shared learning from SERVE/Young Africa model for integral development of underpriveleged young people with specific focus on the franchise model
2012 Result 5.2: Planned for April 2013 - as part of TVET Shared Advocacy Campaign - On Track to be achieved in 2013
2013 Result 5.2: Seminar held in April 2013, with YA Zimbabwe Director, Enet Mukurazita, as guest speaker - attended by 50 people including Irish Aid, Electric Aid & other SERVE donors - ON TRACK
2014 & 2015 Result 5.2: N/A
Target 5.2 Publication of feature on TVET in FaceUp magazine which has an audience of 50,000 secondary school students
2012 Result 5.2: Planned in 2013 as part of TVET Shared Advocacy Campaign - On Track to be achieved
2013 Result 5.2: No publications in FaceUp magazine during 2013 - OFF TRACK
2014 Result 5.2: No publications in FaceUp magazine in 2014 - OFF TRACK
2015 Result 5.2: No publications in FaceUp magazine in 2015 - OFF TRACK
Target 5.2 Irish NGOs and Irish Aid development policies are informed by evidence based learning from the SERVE/Young Africa Model
2012 Result 5.2: Planned for 2013 as part of TVET Shared Advocacy Campaign
2013 Result 5.2: Irish Aid, Electric Aid and RTE One World Fund attended SERVE/YA seminar where learning from YA Model was shared - ON TRACK
2014 Result 5.2: N/A
Target 5.2 Four Shared Advocacy Campaigns are completed reaching a target audience of 12,000 people each year and contributing to progress on the MDG targets for TVET, OVC, HIV/AIDS and
voluntary sector involvment in the development process. |  | Implementation of Designated Website and social media strategy to support the campaigns
2012 Result 5.2 HIV and AIDS Awareness Raising Campaign rolled out in 2012, reaching target audience of 6000 people
Website Section established and social media strategy in place to support campaigns - on track
2013 Result 5.2: TVET Shared Advocacy Campaign completed (seminar, podcast & newsletter) , reaching target audience of 1,000 people
2014 Result 5.2: No advocacy campaign in 2014
2015 Result 5.2: Advocacy limited to awareness raising on issues of OVC, TVET, SDGs with SERVE Network
Underlying Assumptions/Contingencies
Result 5.1: Development education modules require regular review and evaluation to ensure high quality/ Evaluations of dev ed will be taken seriously. SERVE will invest in training leaders and contracting expertise
Result 5.2: (A) SERVE through its new membership of Dochas will actively support the Dochas Act Now Campaign but will also with its four strategic programme partners engage in joint advoacacy on the four specified themes/ The Campaigns will link with
networks and alliances working to futher MDG progress and prioritise offering orientation and education to an audience reachable through the SERVE network and channels.
(B) That Irish NGO's and Irish Aid are keenly interested in developing strategies for engaging young people in the development process in Sub-Saharan Africa.
Sources of Information (All available from SERVE upon request)
Result 5.1: KPI 1: Post volunteer placement evaluation; KPI 2 & KPI 4: Questionnaire completed by SERVE volunteers with robust scoring system, measured Q4 each year; KPI 3: SERVE Solidarity Group records, measured annually
Result 5.2: KPI 1: Annual SERVE review of advocacy work; KPI 2: "Dev Ed" questionnaire, focusing on number of talks, presentations made post placement & SERVE records of Advocacy work;
KPI 3: Annual MDG Progress Report & results of SERVE/partner SDP monitoring; and KPI 4: Interviews, research carried out by SERVE staff in July/August 2013
Footnote 1
"Level of engagement" refers to the contribution returned SERVE volunteers make to the Advocacy Initiatives. This can involve design and implementation of initiatives, participation in events, involving their
network of family and friends etc. This is measured by (1) SERVE'S records of Advocacy Initiatives; and (2) the Development Education questionnaire which is completed each year. We view involvement in Advocacy
Initiatives as a logical progression for some of our volunteers who complete the Development Education programme during placement
Footnote 2
"Progress" refers to the updates provided in the annual MDG Progress Reports. There will be direct correlation to the SDP through the publication of an annual newsletter which will be diseminated to the SERVE network.
The first newsletter, dealing with the 2012 MDG Report, will deal with issues mentioned in point 13 of our Note to Irish Aid which accompanied our first submission of 2013 Results Framework updates (sent 20/02/13)